## Instructions
Instructions: Identify specific environmental review and permitting deadlines and describe how timing requirements will be met for: the completion of any required consultations; the completion of applicable reviews under NEPA, the National Historic Preservation Act (NHPA) Section 106, and the Endangered Species Act (ESA) Section 7; the submission of Environmental Assessments (EAs), if anticipated (note: NTIA will assist in developing an EA schedule if it is determined that a Categorical Exclusion is not applicable); and any required federal, state, and local permits. ISPs should clearly map these milestones within their NEPA schedule and provide anticipated dates for application submission, acceptance, and approval or review completion (MM/DD/YYYY) for each applicable requirement, reflecting typical durations for the anticipated NEPA level and demonstrating a realistic and logically sequenced path to environmental clearance. For every applicable row, complete all required fields: Permit Category, Notes / Description, Permit Name, Governing Entity Type, Authority Having Jurisdiction (AHJ), the three anticipated dates (Submission, Acceptance, Approval), and Renewal Expected. While identification of private authorizations is not required, it is strongly recommended to support a complete and implementation-ready schedule. Rows in this template may be added or removed as needed to accurately capture project-specific permitting pathways and milestones. In addition to the dates in the template, NTIA requires a narrative describing how you will complete consultations, NEPA and Section 106 reviews, and submission of NEPA documentation. For additional guidance on building your milestone schedule, refer to pages 4-7 of NTIA's NEPA for BEAD: Milestone Schedule & NEPA Timeline (linked below). A draft NEPA Milestone Schedule must be submitted to ARConnect within 30 days of executing the Subgrant Agreement. At a minimum, the schedule must address: - The completion of any required consultations - The completion of applicable reviews for NEPA, National Historic Protection Act (NHPA) Section 106, and Endangered Species Act (ESA) Section 7 - The submission of Environmental Assessments (EAs) if anticipated
NEPA for BEAD: Milestone Schedule & NEPA Timeline

## Milestone Template
Permit Category | Notes / Description | Environmental Review and Permitting Phase | Governing Entity Type | Authority Having Jurisdiction (AHJ) | Anticipated Application Submission Date | Anticipated Complete Application Acceptance Date | Anticipated Approval Date | Anticipated Expiration Date | Renewal Expected?
Required Consultations / Reviews
Environmental Review |  | Categorical Exclusion Review | Federal | NTIA / ARConnect ESAPTT reviewer | XX/XX/2026 | XX/XX/2026 | XX/XX/2026 | XX/XX/2026 | Yes/No
Environmental Review |  | Endangered Species Act (ESA) Section 7 | Federal | U.S. Fish and Wildlife Service | XX/XX/2026 | XX/XX/2026 | XX/XX/2026 | XX/XX/2026 | Yes/No
Environmental Review |  | National Historic Preservation Act (NHPA) Section 106 | State | Arkansas Historic Preservation Program | XX/XX/2026 | XX/XX/2026 | XX/XX/2026 | XX/XX/2026 | Yes/No
Environmental Review |  | Environmental Assessment (if applicable) | Federal | NTIA / ARConnect ESAPTT reviewer | XX/XX/2026 | XX/XX/2026 | XX/XX/2026 | XX/XX/2026 | Yes/No
Federal Agency Permits (If Applicable)
Permitting | May require cost recovery agreement. Agency won't begin work until cost recovery in place. Factor into schedule planning | Right of Way (ROW) Permit | Federal | U.S. Forest Service
Permitting | May require cost recovery agreement. Agency won't begin work until cost recovery in place. Factor into schedule planning | Special Use Permit | Federal | U.S. Forest Service
Permitting | May require cost recovery agreement. Agency won't begin work until cost recovery in place. Factor into schedule planning | ROW Permit | Federal | National Park Service
Permitting | May require cost recovery agreement. Agency won't begin work until cost recovery in place. Factor into schedule planning | Special Use Permit | Federal | National Park Service
Permitting |  | ROW Permit | Federal | U.S. Army Corps of Engineers
Permitting |  | Clean Water Act (CWA) Section 10/404 Permit | Federal | U.S. Army Corps of Engineers
Permitting |  | Section 408 Permit | Federal | U.S. Army Corps of Engineers
Permitting | May require cost recovery agreement. Agency won't begin work until cost recovery in place. Factor into schedule planning | ROW Permit | Federal | U.S. Fish and Wildlife Service
Permitting | May require surveys and mapping and Tribal agreements prior to an application deemed complete. | ROW Permit | Federal | Bureau of Indian Affairs
State Permits (If Applicable)
Permitting |  | Section 401 CWA Permit | State | State Water Quality Agency
Local Permits (If Applicable)
Permitting |  | ROW Permit |  | City/County
Permitting |  | Building |  | City/County
Permitting |  | Land Use |  | City/County
Private Authorizations
Private |  | Make Ready Pole Attachments |  | Private